## Einleitung
Einleitung |  |  | Sonstiges
| Dokument Ersteller |  |  | Das Team
Buchberger Christopher
Besteht aus Robert Freiseisen Christopher Buchberger, Egger Sebastian und Aigner Elias
Um was handelt es sich hier?
Hierbei handelt es sich um die Sprint-Plannung für das Projekt Bookless
Kontakt
| Erklräung des Projekts |  |  | Bei jeglichen Fragen oder Change Request wünschen, können Sie sich jederzeit beim mir melden.
| Bookless ist ein EOS Applikation, sprich eine Enterprise Office Software, im deutschen eine Firmen Management Software. Mit den Fokus auf das Customer Realation Management |  |  | Tel. 067762390005
c.buchberger01@gmail.com
|  |  | 272 |  | Buchberger
| Sprint Einteilung |  |  |  | Arbeitsstunden
Die Sprints sind in einzelne Mappen eingeteilt

## Sprint1&2
After checking the Issuses I dealt with in September/November/Dezember
I came to the conclusion that on minimum it took me 120 hours to do solve all the
probably more like 150 hours but the endresult should be a "I worked atleast XX hours" | 120
on this project in 4th grade.

## Sprint3
Todo Stuff | PackageID | Date | Arbeitszeit | WorkPackage | Estimation für Workpackage | Current Estimation | Remaining Time | Description of Task | Arbeit in diesem Sprint
Dashboard Layout | WP1 | 2020-12-14 | 2 | WP6 | 4 | 4 | 2 | The table in customer does not scale when zoom in.
Dashboard Show some data | wp2 | 2020-12-14 | 3 | WP7 | 6 | 3 | 0 | Due to some intern passed data about the customer the user cant route to the edit path via url, so we have to redirect him to the customer list back. | 88
Filter Header for customer list | WP3 | 2020-12-15 | 4 | WP8 | 2 | 4 | 0 | It took some time to deal with some random errors but now we can update a customer
Convert list to company customer | WP5 | 2020-12-16 | 2 | WP1 | 2 | 2 | 0 | The css was a bit tricky but now it works fine. Had to change it a bit
Table using to much space | WP6 | 2020-12-16 | 3 | WP9 | 5 | 5 | 2 | Can show the customer but have, to clean up the code a bit.
Error screen when user tries to edit customer via url | WP7 | 2020-12-16 | 1 | WP9 | 5 | 4 | 0 | Added some regions to make it easier to understand the code, changed the arrangement of the methods added some comments.
Update a customer | WP8 | 2020-12-16 | 2 | WP2 | 2 | 2 | 0 | Currently the current time can be looked up in the dashboard, as well as the top 10 customers, they are not really the top 10 ,since we do not have bills now to rank them with but we can see something…
Show a customer | WP9 | 2020-12-16 | 2 | WPX | 3 | 3 | 1 | Styled some parts of the Dashboard, the Sidenav, the footer , and some other parts of the application to make it look better.
Email A Customer | WP10 | 2020-12-17 | 2 | WP1 | 4 | 5 | 1 | It still have some bugs when changing the zoom setting.
User Rank System | WP11 | 2020-12-17 | 2 | WP1 | 5 | 6 | 0 | Fixed it with a lot of css magic
Blue Theme | WP12 | 2020-12-18 | 4 | WP10 | 10 | 10 | 5 | Created the Email Handler and can send emails to a customer , still have problems sending to multiples customers with diffrent salutations
Create a Order pdf with the basic fields ,like what was bought how much , whats the price the location shipping, date taxes… | WP13 | 2020-12-18 | 2 | WPX | 2 | 2 | 0 | Changed a lot of designs of the, sidenav, the customer table, some parts of the project structure
Do all the stuff thats needed to get the data of an offer and make the pdf dynamic. | WP14 | 2020-12-18 | 2 | WPX | 2 | 2 | 0 | Context menu for the actions of a row of a customer --> add, delete, edit, sent email to
Create the Company customer view ,edit and add page | WP15 | 2020-12-19 | 3 | WP12 | 3 | 3 | 0 | Changed the theme of the application to make it look better
Change all Inputs to material inputs | WP16 | 2020-12-20 | 2 | WPX | 2 | 2 | 0 | Changed the Design of the Footer and Top bar.
Create a "Needed Api request file" with priority listing for the backend team @Robert & @Elias | WP17 | 2020-12-22 | 2 | WPX | 2 | 2 | 0 | Fixed problems in company customer
|  | 2020-12-24 | 2 | WP11 | 2 | 2 | 0 | Added a User rank system, which gives users only the access they should get. We should add that an admin is able to change the premissions of the users
|  | 2020-12-24 | 2 | WPX | 2 | 2 | 0 | Get the user image per base64 and convert it to a showable image file
|  | 2020-12-25 | 2 | WPX | 2 | 2 | 0 | Design of Profile Page (is still not zoom resistend)+ premission for settings page + admin panel in the Profile Page
|  | 2020-12-25 | 2 | WP13 | 15 | 15 | 13 | Tried jsPdf, but switched to pdfMake --> more features, easier to use, more tutorials on it. Currently we can view and download a generated pdf thats says "I am a order."
|  | 2020-12-25 | 2 | WP13 | 15 | 15 | 11 | Created the Product Service to get the Order product data, can display the products with the prices in the pdf, but no style inside the pdf
|  | 2020-12-25 | 3 | WP13 | 15 | 7 | 0 | Created the Pdf for an Offer, currently it's still static but, thats what this tasks wants me to do. See the current Design on the right. Pdf was coded with JSON via pdfMake
|  | 2020-12-26 | 1 | WP11 | 2 | 2 | 0 | Before it was only possible to have all premissons on a part of the application or none at all now you can have none, read and write premissions!
|  | 2020-12-26 | 1 | WP14 | 15 | 15 | 14 | Copy pasted the customer table into the productcomponent and changed the columns to match the IRawProduct interface. Changed the styling to fit.
|  | 2020-12-26 | 1 | WP14 | 15 | 15 | 13 | WIP: Product Table actions component + detection which modes the user is currently in + data insertion into component
|  | 2020-12-26 | 1 | WP14 | 15 | 15 | 12 | Created the interface for an order used 'Tresor Warenwirtschaft' as reference on what data should be displayed.
|  | 2020-12-26 | 3 | WP15 | 3 | 10 | 7 | Firstly i thought it would be pretty easy, but the fact that we have multiple arrays inside a company e.g order adresses, contact persons ,makes the designing process sky rocketing
|  | 2020-12-26 | 2 | WP15 | 10 | 7 |  | After struggelling with using ngModel inside a ngFor with an array inside an object and creating a uniqe name for each input, we can update a company customer (but we cant add one currently :D) The component needs some more styling and the add feature
|  | 26.Dez-27.Dez | 3 | WP15 | D:\Git\bookless\Frontend\src\models\bill\offer\OfferData.ts | 10 | 2 | Add feature - angular converts the type inside a ngfor to compare them, this breaks when using a array with primitive types like strings, numbers etc. After 2+ hours changing settings and doing magic, i managed to get the add to work. Needs some refactor now + styling
|  | 2020-12-27 | 1 | WP14 | 15 | 15 | 11 | Created a sketch of the Order table, the green and red fields indicate whter an offer has been transformed into an order a bill and wheter ist finished. Screenshot on the right.
|  | D:\Git\bookless\Frontend\src\models\bill\offer\OfferData.ts | 2 | WPX | 2 | 2 | 0 | WIP Redesign of the Profile Page. The password inputs can now be toggled to show or hide the content. The inputs use in generel now a more modern design.
|  | 2020-12-27 | 2 | WPX | 2 | 2 | 0 | Currently chaning the Profile page to make it fit better into the appliaction and make it more modern.
|  | 27.Dez-28Dez | 3 | WP14 | 15 | 12 | 5 | Creating mock data for offers- creating offer table, chaning pdf service to inititalize all the data thats given into it, populating the data inside the pdf with the data. Change diffrent parts of the pdf wheters it's an company or an private customer. creating big jsons to help filling data into it, due to the 2 types of customers company and private , they have diffrent fields.
|  | 2020-12-28 | 3 | WP14 | 12 | 15 | 5 | I got real pdfs including offers, bills orders etc. from Powersolar and now i change the design to fit the current offer more. Background color, is something pdfMake is really bad in….
|  | 2020-12-28 | 2 | WP14 | 15 | 15 | 3 | Was able to create the wished border, it was really hard to work arround the limitation, of pdfMake.
|  | 2020-12-28 | 1 | WPX | 1 | 1 | 0 | Some changes here , some there, a bit style here and some magic in the profile design
|  | 2020-12-28 | 3 | WPX | 3 | 3 | 0 | Reworking the profile page again moving data underneath the profile picture and create a extra setting page for further customization for the user.
|  | 2020-12-29 | 2 | WPX | 2 | 2 | 0 | Changing Profile page routed to the setting page, changed the IofferInterface to fit the new data structure.
|  | 2020-12-29 | 2 | WP14 | 15 | 16 | 2 | Changed all the Interfaces to match, loaded new data, put the new data inside the pdf, maybe some small design changes, but pdf looks nice. Need to talk with some PowerSolar employee about the Order Id, and how its connected in the whole system.
|  | 2020-12-30 | 2 | WP14 | 16 | 16 | 0 | Talked with PowerSolar Devs about the Offer, finished the last small parts and pushed the finished Pdf Generator
|  | 2020-12-30 | 2 | WP15 | 15 | 14 | 0 | Added the last fields into the mask.

## Sprint4
Todo Stuff | PackageID | Date | Arbeitszeit | WorkPackage | Estimation für Workpackage | Current Estimation | Remaining Time | Description of Task | Arbeit in diesem Sprint
Ui Changes | WP1 | 2021-01-07 | 4 | WP1 | 4 | 4 | 0 | Changed a lot of Ui elements due to some changes in the data structure of the Order data
Fix the Customer NULL Bug | WP2 | 2021-01-08 | 3 | WP2 | 1 | 7 | 5 | I have no idea where the problem is… | 21
Fix Delete Bug | WP3 | 2021-01-14 | 3 | WP2 | 6 | 6 | 3 | Fixed the null bug it was due to some fields that were not inside a private customer object, i need to make them editable inside the private customer data object.
|  | 2021-01-15 | 3 | WP2 | 6 | 6 | 0 | After chaning the customer data and some rework of the pdf generator we now can create a private customer order pdf
|  | 2021-01-15 | 3 | Wp1 | 3 | 8 | 1 | Changed the private customer input mask
|  | 2021-01-16 | 2 | Wp1 | 8 | 8 | 0 | Changed the private customer input mask
|  | 2021-01-17 | 1 | WP3 | 6 | 3 | 0 | The datasource only had the current page so when we set it as new data we cut everything that is not on the current page.
|  | 2021-01-18 | 2 | WP2 | 6 | 4 | 0

## Sprint5
Todo Stuff | PackageID | Date | Arbeitszeit | WorkPackage | Estimation für Workpackage | Current Estimation | Remaining Time | Description of Task | Arbeit in diesem Sprint
Transformation System Idea | WP1 | 2021-01-22 | 1 | Wp1 | 1 | 3 | 2 | Well, we need a system that can use a huge json and create a differnt pdfData object out of it
Transformation Dialog | WP2 | 1900-01-22 | 2 | Wp1 | 3 | 3 | 2 | Like previously planned thats gonna be the way | 41
Transformation Offer --> Order | WP3 | 2021-01-24 | 2 | WPX | 2 | 2 | 0 | Found bugs with the routing data fixed those and styled offer data component a bit more
Offer Data Add Delete Bugs | WP4 | 2021-01-25 | 2 | WPX | 2 | 2 | 0 | More css styling and some code rework
Offer List css styling | WP5 | 1900-01-25 | 2 | Wp2 | 4 | 5 | 3 | Im not sure why but using Mat-dialog is one of the worst things to do in angular, because you will always have a lot of trouble just creating it
Change Transformation System | WP6 | 1900-01-26 | 3 | Wp2 | 5 | 5 | 0 | After even more troubles the Dialog is kind of finished need some more css styling, but firstly the Transformation function is important
Fix electron | WP7 | 1900-01-27 | 2 | Wp4 | 4 | 4 | 2 | After Debugging a lot i was able to fix the delete bug, but some weird stuff still can happen, not sure why but sometimes a row gets now added double…
IOfferData rework | WP8 | 1900-01-29 | 4 | Wp4 | 4 | 4 | 0 | Fix it in some weird cases, it was possible that the filterd list contained the entry twice, not sure why but i had to change the whole add system
Publish the Project on GH | WP9 | 2021-02-01 | 2 | Wp5 | 2 | 2 | 0 | Had to reworks eggers last sprint Issue 64 due to a not that great looking user experience.
|  | 2021-02-03 | 2 | Wp6 | 2 | 2 | 0 | Changed to a single entry point system
|  | 2021-02-04 | 3 | WP7 | 5 | 3 | 0 | Me and Egger were able to find a solution to the Electron build error somehow the main.js was deleted and the dist folder were not build again.
|  | 2021-02-06 | 2 | WP8 | 2 | 2 | 0 | After some problems with the services the rework is finished.
|  | 2021-02-07 | 2 | WPX | 2 | 2 | 0 | Reworked the Excel sheets especially the sprint sheet (this one) and the sprint meeting one.
|  | 2021-02-08 | 3 | WP9 | 2 | 3 | 0 | After watching some YT Videos and trying it, i was able to Puplish it under following URL https://codechrisb.github.io/bookless
|  | 2021-02-12 | 2 | WPX | 2 | 2 | 0 | Pdf Generation System rework
|  | 2021-02-14 | 2 | WPX | 2 |  | 0 | I tried to change the dashboard css so that the boxes would still fit even when the left sidenav was gone ,since Im aiming to change the current nav with a mat sidenav to give the user more space if he/she wants it.
|  | 2021-02-18 | 3 | WPX | 3 | 3 | 0 | Some changes on the pdf Generation unrelated to any particular Issue
|  | ? | 2 | WP9 | 2 | 2 | 0 | Im not sure when I published the Live demo but it took me about 2 Hours

## Sprint6
Todo Stuff | PackageID | Date | Arbeitszeit | WorkPackage | Estimation für Workpackage | Current Estimation | Remaining Time | Description of Task | Arbeit in diesem Sprint
Bill Pdf Generation | WP1 | WPX | 2 | 2 | 2 | 2 | 0 | Talking about new Sprint creating the first half of the power point for this sprint, sprint meeting
Delivery Note Component | WP2 | [7 empty] | 2
Delivery Note List | WP3
Delivery Note Pdf Generation | WP4
Transformdialog all the Transformation | WP5

## Sprint7
Todo Stuff | PackageID | Date | Arbeitszeit | WorkPackage | Estimation für Workpackage | Current Estimation | Remaining Time | Description of Task | Arbeit in diesem Sprint
0

## Sprint8
Todo Stuff | PackageID | Date | Arbeitszeit | WorkPackage | Estimation für Workpackage | Current Estimation | Remaining Time | Description of Task | Arbeit in diesem Sprint
0

## Sprint9
Todo Stuff | PackageID | Date | Arbeitszeit | WorkPackage | Estimation für Workpackage | Current Estimation | Remaining Time | Description of Task | Arbeit in diesem Sprint
0

## Sprint10
Todo Stuff | PackageID | Date | Arbeitszeit | WorkPackage | Estimation für Workpackage | Current Estimation | Remaining Time | Description of Task | Arbeit in diesem Sprint
0